## Sheet1
Gantt Chart - Walk/Bike/Transit Project 2011-2012 | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec
Food Security Committee decided on Climate Change as the social justice ellement of food security in Nicaragua | bar: May to July
Volunteers work with staff to develop an outline for the Walk/Bike/Transit campaign | bar: May to Aug
Full NHSCP discussed and approved the initial Walk/Bike/Transit | bar: Sept
Campaign information up on out website (expand and update throughout the year) | bar: Sept to Sep
Core Volunteer Team Established | bar: Sept
Core Volunteer Team Meetings (biweekly) | bar: Sept to Sep
With design intern, develop campaign materials (logo, brochure, T-shirt design, PSAs); finalize posters, postcards | bar: Sept to Nov
Develop and finalize detailed campaign strategy for Winter and Spring | bar: Nov to Dec
Hire part-time staff (dependant on grant funding-GNHGF) | bar: Nov to Dec
Tabling (biweekly) market research questionnaires to inform future campaign decisions (every two weeks) | bar: Sept to Nov
Tabling (biweekly) transportation, climate change, and food security facts | bar: Sept to Sep
Tabling (biweekly) sustainable transport new year's pledge (to reduce car use by either 5, 10, or 15 percent in 2012) | bar: Nov to Dec
Public art and events (at least once/mo) | bar: Oct to Sep
Teach-ins (at least one every two months) | bar: Oct; Dec; Feb; Apr; June; Aug to Sep
Media and PSAs (posters every two months, bus/transit ads up longer) | bar: Oct to Sep